## Sheet1
S. No. | Program | Duration | DCBL Stake Holder | KiE Stake Holder | Week | Data Status | Solutioning | Feedback | PoC/Report | Feedback | Feedback Incorporated | Final Solution | Solution Integration | WSR | Key Milestone
1 | SALES TARGET ALERT |  |  | Abdul |  |  | Yes | TBS | WIP
2 | SALES DRAG PARETO |  |  | Sainath |  |  | Yes | TBS | Ready
3 | PRICE INDEXING |  |  | Abhishek |  |  | Yes | TBS | Ready
4 | VC BRIDGE |  |  | Saad |  |  | Yes | Partial | Ready
5 | DEALER PLAYBOOK |  |  | Tishunk |  |  | Yes | TBS | WIP
6 | DEALER CHURN |  |  | Nikhil | 29May-02Jun | Data used: Sales Data, Non Billing reason Data | Yes | Partial | Ready | [5 empty] | YOY-QOQ analysis done, Dashboard wireframe ready.
7 | PRICE DISCOUNT |  |  | Pankaj |  |  | Yes | Yes | Delivered |  | WIP
*Needs to be updated in the future because of Data Gaps
3 | PRICE INDEXING |  |  | Abhishek | 05-09 Jun | Data used: Price_PD_WSP_Apr_22-Feb_23_with_QTY_ASO | Yes | Partial | WIP | [5 empty] | Created dashboard wireframe, Interactive Dashboard ready